## Milestone - 14
Date | Task | Total Time | Time in Mins | Note | PHP Task | Total Time | Time in Mins | Note
2023-06-20 | -Set up two new api for sending the the withdrwal messege to the admin -Create the functionality if the user want to withdraw his winning then the withdrwal messege send to the admin -Modify the ui of the withdrwal pannel (01:45) -Create the functinality when user put his credentials of paypal then the credentials will store in the database -Improve the quality of the images in the reel (1:00) -Fix the issue of fb coins add continuasly in database(make it one time per user) -Make the build of game and test the functionality (01:00) | 0.15625 | 225
2023-06-21 | -Implemented withdraw request and paypal details save api -Save the paypal credentials into the database and by using them send the messege to the admin panel (00:30) -fix the issue of data is not storing properly into the database (02:00) -fix the issue of fb coins add continuasly in the game -check the admin panel by sending the api detalis from the postman application and create user in admin panel (01:20) | 0.15972 | 230 |  | * API - Save user's paypal detail - Generate withdraw sweepcoin * Admin panel - Withdraw sweepcoin management => List the requested withdraw sweepcoin => Accept the withdraw request | 2:20 | 140
2023-06-22 | -Fix the issue of user payment credentials not storeing in the database -Improve the ui of withdrawl panel and top up pannel -Test the admin panel whare all the data is storing (by sending data from the game ) (1:45) -Create build of the game and test (00:30) -In test i found that if we relogin again and again then every time 200 coins add to the coins for fixing this issue i test the api and found that every time api call 200 coins come from the api working on the issue of data storing in database (02:15) | 0.1875 | 270
2023-06-23 | -Work on the coin data storing in database(00:30) -In testing i found that the data is updating properly but when user relogin again and again user ger coins multiply by 2 every time -Then backend team add new boolean parameter to api .implement that new api in game and by that arameter fix the issue of user get double coins (1:00) -Add the coins data in the database -Fix the issue of coin data not add properly in the database( coins adding in the database with the addition of previous data) (01:00) -Create the functionality to add coins data from the database to the ui at a run time (01:00) -Fix the issue of coins are not refreshing properly in the ui(coin are refreshing by delay of one operation) -Build the game and test all the functionality (01:15) | 0.17708 | 255
2023-06-24 | -Work on the issue of coins not updating after user login in the facebook(coins update in database but not in ui) -Work on stop rotation of slots when no button is press (01:00) -Genrate pop-up when user did not select any button (sweep coin , gold coin button) -Stop slot rotation when user not have sweep coin balance -Genaret pop-up of (you have no money) when user did not have coins -Build the game and basic test (1:00) | 0.083333 | 120
Total |  | 0.76389 | 1100 Mins |  |  | 0.097222 | 140 Mins
| GrandTotal (Design + PHP) | 0.86111
Formulas:
Total Time = SUM(C2:[Total Time, row above])

## Milestone - 13
Date | Task | Total Time | Time in Mins | Note | PHP Task | Total Time | Time in Mins | Note
2023-06-13 | -Implemented logic for handling response from Api (00:45) -Implemented logic for triggering api at different events (1:15) | 0.083333 | 120
2023-06-14 | -Store the value of coins and sweepcoins in the playerprefs for call the value of coins in api -create the functionality of seting the social login api when user login into facebook and all other api after login into the facebook (1:15) -Fix the issue of coins not showing in the api -Set the api for level and logout | 0.083333 | 120 |  | - Admin panel developement - Login page - Dashboard page - User management - User list page - Edit user - Delete user - Search user - Acvtiv/Deactive user | 2:30 | 150
2023-06-16 | -Store the data into prefabs and call from the database when user login into facebook (01:00) -Solve the error of get method in api -Fix the isuue of coin not updating from the database (1:00) -Make the build of game for testing (Find that when user login into facebook then its data will save in databse and after that he can call there data when they start new gameplay) -Working on the previous data lose when user login into facebook(work in progress) (1:30) | 0.14583 | 210
2023-06-17 | -Work on to get the previous data from the login -Add the fb coins into the current coins (1:15) -Store the coin values after you login into the facebook and after that save the data in database so ehen we relogin into another devise so we get our data back -work on the reel speed should land in staggered approach from left to right -Work on the reel image to show up to the user face really big so user could see artwork and card better (1:45) -Make the build and basic test the game (1:30) | 0.1875 | 270
Total |  | 0.5 | 720 Mins |  |  | 0.10417 | 150 Mins
| GrandTotal (Design + PHP) |  | 0.60417
Formulas:
Total Time = SUM(C2:[Total Time, row above])

## Milestone - 12-done
Date | Task | Total Time | Time in Mins | Note | PHP Task | Total Time | Time in Mins | Note
2023-05-31 | Add font and background image in ui of sweep coins -Add topup button to sweep coin panel (by pressing topup button we get 5000 coin and we can use them by selecting sweep coin button in the game scene) -Add withdraw button to sweep coin panel (withdraw can only be intractable when user have 50 or more coins and by pressing withdraw button user can withdraw 50 coins) -Fix the isuue of coin not updating when user win the coin | 0.16667 | 240
2023-06-02 | - Create ui panel for payment gateway and add input field for taking input by user for the payment details(15 min) - Make ui of payment gateway respnsive and functional (2:00 hours) - Add the functionality of take data from user and store locally(playerprefs)(45 min) Ex (when user login in facebook he get a popup of payment gateway where he can fill his credentials and that credentials will be used for money transaction in future) - Add the skip button functionality Ex (if the user did not want to give there data in payment gateway then they can skip that section) - Add the check credentials functionality in sweep coin panel Ex ( if user not submit his credentials at the time when he login in the facebook then in sweep coin panel when user want to withdarw his money and he click withdraw button he get the pop up of payment gateway . If he already submited the credentials then he did not get the popup his money transfer request send to the backend) | 0.125 | 180
2023-06-03 | -Do some changes in ui of sweep coin panel and and pament gateway panel -Create new popup panel that only show up when user did not login in the facebook (1:00 hour) -Make the ui Functional and working by adding new function to the withdraw button (00:45 minutes) Ex (if the user did not log in facebook and try to withdraw coins then the popup shown with text (for example please login for playing with sweep coins)) -Watched refrence video of "chumba" and understand the basic flow, how the money system works in it.(00:30 minutes) | 0.09375 | 135
2023-06-06 | -Create new ui of shop menu for sc coins(00:30) -Add vertial layout component in ui to show shop ui verticaly(00:30) -Make the dynamic data of sc coins for shop menu(00:30) -Create the functionality to show the data in shop menu by script(01:00) -Working on the add coin in sc by the pay table(work in progress)(01:00) | 0.14583 | 210
2023-06-07 | Improve the shop panel ui -Add new variable to the paytable of sc coin by which we can add sc won coin dynamicaly (00:30) -Create functionality for add sc coin dynamialy when user win the line (01:00) -Create functionality when user play with gold coins it did not effect on sc coins and vice-versa -Fix the issue of sc coins not adding by paytable (01:30) | 0.125 | 180
2023-06-08 | -Fix the issue of sc coin is adding in gold coins -Create and test the apk (I put the link of game above please inform us about the changes) (1:00) | 0.041667 | 60
2023-06-09 |  |  |  |  | - Project Setup - Database Setup - Create Social Login API - Create Set Coins API - Create set SweepCoins API - Create get Coins API - Create get Sweep Coins API - Create get User Detail API - Create Update Level API | 4:45 | 285
2023-06-10 | -Implemented basic logic for calling following webservices -Social Login -Set Coins (1:30) -set SweepCoins -get Coins -get Sweep (1:00) -get User -Update Level (1:00) | 0.14583 | 210
Released on 16/060till 10/jun
Total |  | 0.84375 | 1215 Mins |  |  | 0.19792 | 285 Mins
| GrandTotal (Design + PHP) | 1899-12-31 01:00
Formulas:
Total Time = SUM(C2:[Total Time, row above])

## Milestone - 11-done
Date | Task | Total Time | Time in Mins | Note
2023-05-22 | -Add new particle efect for the animation of screen effect -Add new animation for winning free Spin -Add the functionality to present the freespin animation when user get free animation -Working on improving animations(Inprogress) | 0.125 | 180
2023-05-24 | -Add new animation for indicating free Spin (scaling) -Add the functionality to present the freespin indication animation when user get free spins | 0.10417 | 150
2023-05-26 | -put the UI images with the size require in the file -Also i put the sounds that is currently using in a game -Plese create sound acoording to the details that i provided in the pdf | 0.041667 | 60
2023-05-30 | - Watch the refrence video -Add new panel for sweepcoin and also add ui text and buttons -Create functionality for updating sweepcoin value according to the game -Create such a button that if gold coin button is selected then it will update gold coin and if sweep coin button is selected then sweep coin will update | 0.14583 | 210
Released on 05/06/2023 by d sir till 30th ma
|  | 0.41667 | 600 Mins
Formulas:
Total Time = SUM(C2:[Total Time, row above])

## Milestone - 10-done
Date | Task | Total Time | Time in Mins | Note
2023-05-18 | -Worked on updating button animatoins as shown in reference video -Working on improving animations in gameplay(Inprogress) | 0.083333 | 120
2023-05-19 | -Add some new buttons in ui -Create a functionality for continually change the color of sprite of buttons -Research on using real currency in game | 0.14583 | 210
|  | 0.22917 | 330 Mins
Formulas:
Total Time = SUM(C2:[Total Time, row above])

## Milestone - 9-done
Date | Task | Total Time | Time in Mins | Note
2023-04-18 | ->Added facebook sdk in project for implementing facebook login ->Added dummy client app id and token (We need to create App Id for our FPK game) ->Implemented logic for facebook login ->Implemented logic for reading user name and saving in local storage ->Added message screen that displays the user's name and message for 100 coins reward ->Implemented logic for adding 100 coins reward only one time for user. ->Added Logout button functioanlity | 0.1875 | 270
2023-04-20 | ->Added scripts for In-App purchase handling ->Implemented logic for In-App purchase items (5000 coins ,10000 coins, 20000 coins, 40000 coins) ->Implemented logic for setting in-app purchase functionality runtime ->Worked on storing player data in local device | 0.16667 | 240
Released on 08/05/2023 by d sir till 20 aprril
|  | 0.35417 | 510 Mins
Formulas:
Total Time = SUM(C2:[Total Time, row above])

## Milestone - 8-done
Date | Task | Total Time | Time in Mins | Note
2023-02-25 | ->Change Text Size of coin amount, total bet, hold to spin, win, info and lobby. ->Add Outline for all text. ->Change color of all text. ->Change info And lobby button's position. ->Set allthings responsive and clear for better experience. ->Build and basic testing | 0.14583 | 210
2023-03-10 | ->Check audios in the game. ->Added background Music in game scene. ->Replaced audio clips for slot rotation , slot loose, Bat buuons,menu pop-up , Win coins. ->Create and test build. | 0.10417 | 150
2023-04-04 | ->I have tested free spin functionality with static value 1 spin for any combination of line and found that free spins given to player as reward (see attached videos) ->While testing I found that when there are many matches (many lines) ,the existing logic animates for each matching line and then coins added.When all the animations are completed the spin is allowed. ->Worked on increasing the speed of animation and updated the animation for matching lines (Jump animation) | 0.14583 | 210
|  | 0.39583 | 570 Mins
Formulas:
Total Time = SUM(C2:[Total Time, row above])

## Milestone - 7-done
Date | Task | Total Time | Time in Mins | Note
2023-02-21 | ->Replaced new background in splash/Lobby screen. ->Add new logo in splash screen. ->Added new frame in game scene for visualization. ->tested changes in device | 0.125 | 180
TOTAL |  | 0.125 | 180 Mins
Formulas:
Total Time = SUM(C2:[Total Time, row above])

## Milestone - 6-done
Date | Task | Total Time | Time in Mins | Note
2022-11-02 | ->Added missing raycast references and fixed spin not working after 3/4 spins. ->Removed old circular win effect. Added square transparent effect. ->Removed background from popups ->Working on paytable and popup contents.(Inprogress) | 0.15625 | 225
2022-11-07 | ->Added new logo image in game ->Searched fonts similar to "garbage pail kids" ->I have attached three fonts sample text image. Please check if we can use any one of it. ->Working on info panel UI changes and paytable changes (Inprogress) | 0.16667 | 240
2022-11-08 | - Export to xcode build, - Added shared UDID to developer account, - Create ios build - Test on physical device - Upload build and share link to install build | 0.03125 | 45
2022-11-09 | ->Updated paytable settings ->Updated rewards for special symbols ->Updated rewards for noraml cards ->Working on other info popups changes (Inprogress) | 0.16667 | 240
2022-11-10 | ->Changed following information popup UI --Major symbols description --Special symbols description --Palylines description --Help -description ->Updated text fonts in game screen ->Removed old "SPIN" text from image and created blank image ->Added "SPIN" text with new font in "SPIN" button ->I have recorded video with updated font. | 0.16319 | 235
2022-11-12 | ->Updated font in game screen and info popups ->Updated UI of lobby screen ->Updated fonts ,removed backround images in popup from lobby screen ->Added 10 free spins for 5 bonus in a line ->Updated pay table for giving free spins for "Free Spin" count 3 ,4 or 5 in a line ->Recorded video, please check it. | 0.12847 | 185
2022-11-15 | ->Increased default coins value for testing ->Added Temp button "Add Coins" in lobby ->Build android apk and basic testing | 0.013889 | 20
Released on 16/01 by d sir till 15 nov
TOTAL |  | 0.82639 | 1190 Mins
Formulas:
Total Time = SUM(C2:[Total Time, row above])

## Milestone - 5-done
Date | Task | Total Time | Time in Mins | Note
2022-10-08 | -Implemented new rectangle shape mask image in the game. -Updated collider shapes from circle to rectangle for slot items. -I found that after the first speen, the slot items not set properly in some reels.It may be because we have increased the number of items displayed in reel. -Worked on this issue to fix it (Inprogress) | 0.086806 | 125
2022-10-22 | -Worked on reel spin issue. -Set 30 icons limit and fixed reel icons position issue after first spin. -Increased icon sizes -Updated splash screen image -Build apk | 0.024306 | 35
2022-10-28 | -Switch game platform to webgl -Build Webgl version of game. | 0.024306 | 35
2022-10-29 | -Worked on Webgl version -Removed logo from splash screen to avoid multiple views of company logo. -Worked on fixing webgl portrait mode issue.(Inprogress) | 0.069444 | 100
TOTAL |  | 0.20486 | 295 Mins
Formulas:
Total Time = SUM(C2:[Total Time, row above])

## Milestone - 4-done
` | Task | Total Time | Time in Mins | Note
2022-09-12 | -Rearranged the UI of 3x5 game -UI menu responsive settings impemented -Background set in 2D -Updated camera settings for displaying background -Set reel display in the center area of the bottle. -Working on reel icon display to increase hight and width of reel icons. -I have attached video of the updated look of 3X5 game. -Please provide your feedback on the arrangement of buttons and other text display. | 0.16667 | 240
2022-09-13 | -Set "Spin" button in the bottom middle of the pill bottle. -Set "Total Bet" on left side of "Spin" button and "Win" on right side of the "Spin" button. -Set company logo as App icon. -Implemented logic for setting reel center point in the center part of PillBottle's black area. -Removed circular front mask from the reel icons. | 0.11458 | 165
2022-09-14 | -Trimmed transparent part of free spin frames. -Created animation for new freee-spin and implemented in game. -Imported character-pack images in project and sliced characters from images. -Added character images as reel icons. -Implemented logic for hiding the backside icons displayed on reel. | 0.16319 | 235
2022-09-17 | -Updated slot controller icons group, added all the character-cards in slot controller -Updated reel-icon list for each reel -Ready made code is set to display 16 icons. -Worked on updating code to display 40 icons. -I found that after first speed icons are not properly positioned in second speed.Working on it(Inprogress) | 0.12847 | 185
2022-09-19 | -Imported new background image in project -Replaced current pink background with new background -Set reel center point as per new background -Working on reel icon resizing(Inprogress) | 0.072917 | 105
0
0
TOTAL |  | 0.64583 | 930 Mins
Formulas:
Total Time = SUM(C2:[Total Time, row above])

## Milestone - 3-done
Date | Task | Total Time | Time in Mins | Note
2022-08-29 | - Downloaded reference packages provided by you. - Can not open the packages as they are not related to unity - Crated UI asset link and sent to you. - Discuss with you on reskinning - Fixed Uxml UI package error in Aqua-slot game package. | 0.125 | 180
2022-09-01 | Discuss and check shared documents and new images | 0.020833 | 30
2022-09-02 | - Imported graphics in project. - Replaced slot icons with new icons (fpk 1 to 12) - I found the the size of sprites for reel icons does not feet in the UI. - I have resized reel icons from size (750x1050) to (250x350). - Replaced Main screen background and 3x5 game background. - I have attached video of main screen and the 3x5 screen. | 0.1875 | 270
2022-09-03 | - found and fix responsive issue in editor - Build the apk and checked UI - Worked UI responsive issue in asset(Inprogress) | 0.0625 | 90
2022-09-06 | - Implemented logic for displaying animated slot icons - The original asset does not have animator on slot icon prefab. - Added animator component to slot icon prefab and implemented logic for enabling animator component for special icons. - We need to implement frames - Working on UI related tasks. | 0.16667 | 240
2022-09-08 | -Created frames from .mp4 files for scatter,wild and free-speen animations. -Resized images and implemented frames in animation clips -Implemented logic for playing respectiv animation clip for animated icons in Reel. -I have attached video of animated icons in game. -Please provide fonts and other graphics you want to use in game. | 0.11806 | 170
2022-09-10 | -Removed bubble from the art work -Space set to black behind the reels -Added "FENTANYL PATCH KINDS" text in top -Removed aqua theme button sprites -Working on UI to keep the reel-icons/artwork with in the black area of the bottle with different screen size(Inprogress) -I will share you video with updated UI soon. | 0.13889 | 200
TOTAL |  | 0.81944 | 980 Mins

## Milestone - 2_done
Date | Task | Total Time | Time in Mins | Note
2022-08-23 | Setup for basic things for the portal (in progress) | 0.125 | 180
2022-08-24 | Setup for basic things for the portal (in progress) | 0.20833 | 300
2022-08-25 | Setup for basic things for the portal (in progress) | 0.16667 | 240
2022-08-26 | - Discussion with you, - Find slot machine game code and verify in Unity | 0.14583 | 210
2022-08-27 | - Imported different slot machine codes and checked in editor. - I found the "Aqua slot" game asset useful to us. - I have fixed version upgrade errors. - Capture and share video of game. | 0.20833 | 300
|  | 0.85417 |  | Released on 05/09 by d sir
0
0
TOTAL |  | 0 | 1230 Mins
Formulas:
Total Time = SUM(C9:[Total Time, row above])

## Milestone - 1_done
Date | Task | Total Time | Time in Mins | Note
2022-07-20 | - Basic design for website main page | 0.125 | 180 | Designer work
2022-07-27 | - Login , Register, Forgot password pages design | 0.059028 | 85 | Designer work
0
0
0
0
0
0
0
0
0
TOTAL |  | 0.18403 | 265 Mins
Released on 27/08 by d sir we havwe advance 20.5 hours
Formulas:
Total Time = SUM(C2:[Total Time, row above])